IV.	Goals and Action Plan

| Goals | Date to Complete | Leadership Team |
| --- | --- | --- |
| A. COMMUNICATION |  |  |
| Work through PLP to clarify meeting regulations under the Brown Act, including videoconferencing. | By June 2011 | Jayanti Addleman and PLP Staff |
| Adopt meeting guidelines and procedures that provide for remote meeting attendance (e.g., tele/video conferencing). | Recommendations and Plan to the Administrative Council by June 1, 2011 Goals: A.2 & C.1 – Taskforces may be combined. | Task Force with one representative of each committee and Administrative Council Teresa Landers (for legal questions) Eleanor Uhlinger, Admin., Stacey DeMatteo, Bill Rawson |
| Appoint a task force to propose content, design and maintenance recommendations, and cost estimates for a re-designed website. Ensure that the new design incorporates fast and easy methods and tools for individual staff members to update data. Explore incorporating access to MOBAC- created archival materials on the website, a training library, and a directory of staff specialized skills and knowledge. | By July 2011 | Task Force with representatives of each committee and Administrative Council Georg Romero, Admin. James Ghiorzi; Website Maintenance, Irene Berry, Jean Chapin, Steve Watkins Donna Truong, PLP Rep. |
| B. STAFF DEVELOPMENT |  |  |
| Create a MOBAC-wide staff development plan: Identify best practices for assessing staff development needs (e.g., survey staff about content areas of interest; address barriers to participation, etc.); Use internal (MOBAC), as well as external resources for training and other staff development options; Improve the dissemination of and access to information about professional development options; Create a directory of staff with specialized skills and/or knowledge to be posted on the website. | By June 2012 | Task Force with representatives of each committee and Administrative Council Lisa Maddalena, Admin., Heather Geddes, Chris Ricker, Monica Wilmot |
| Explore options, including legal requirements, test alternatives, and develop a plan for recording and archiving training sessions for future viewing and use, including those offered by PLP. Include in the study the creation of a training library on the website. | February 2012 | Technology Committee |

| Goals | Date to Complete | Leadership Team |
| --- | --- | --- |
| C. TECHNOLOGY |  |  |
| Investigate technology for remote attendance to meetings and other service delivery options (workshops, etc.) Explore options and funding for all member libraries to have access to the necessary tools to participate remotely. | By February 2011 See A2. | Task Force with representatives of committees and the Administrative Council Technology Committee, Bill Rawson, Stacy DeMatteo |
| D. FUNDING AND ADVOCACY |  |  |
| Negotiate with PLP the sustained support for regional (MOBAC) activities, including grants. | Ongoing | Jayanti Addleman and PLP staff |
| DRAFT formal guidelines and tools for advocating for library services within the MOBAC region. | June 2012 | Administrative Council Task Force led by Kim Bui-Burton MegaMeeting, Teresa Landers, Peggy Mayfield |
| Conduct a cost-benefit analysis of the PLP contract and other MOBAC expenses. | October 2012 | Budget Committee |
| E.. LOCAL IDENTITY |  |  |
| Develop criteria and guidelines for creating committees. | June 2012 | Administrative Council / Committees Task Force Council Chairs Peggy Mayfield & Comm. Chairs |
| Develop a position statement regarding resource sharing as a core function of MOBAC. | August 2012 | Jayanti Addleman, Ginny Steel and Kim Bui-Burton |

- =completed