IV.	Goals and Action Plan

| Goals | Date to Complete |  | Leadership Team |
| --- | --- | --- | --- |
| A. COMMUNICATION |  |  |  |
| - Work through PLP to clarify meeting regulations under the Brown Act, including videoconferencing. | - By June 2011 |  | Jayanti Addleman and PLP Staff |
| - Adopt meeting guidelines and procedures that provide for remote meeting attendance (e.g., tele/video conferencing). | - Recommendations and Plan to the Administrative Council by June 1, 2011 Goals: A.2 & C.1 – Taskforces may be combined. |  | Task Force with one representative of each committee and Administrative Council Teresa Landers (for legal questions) Eleanor Uhlinger, Admin., Stacey DeMatteo, Bill Rawson |
| - Appoint a task force to propose content, design and maintenance recommendations, and cost estimates for a re-designed website. - Ensure that the new design incorporates fast and easy methods and tools for individual staff members to update data. - Explore incorporating access to MOBAC- created archival materials on the website, a training library, and a directory of staff specialized skills and knowledge. | - By July 2011 |  | Task Force with representatives of each committee and Administrative Council Georg Romero, Admin. James Ghiorzi; Website Maintenance, Irene Berry, Jean Chapin, Steve Watkins Donna Truong, PLP Rep. |
| B. STAFF DEVELOPMENT |  |  |  |
| - Create a MOBAC-wide staff development plan: - Identify best practices for assessing staff development needs (e.g., survey staff about content areas of interest; address barriers to participation, etc.); - Use internal (MOBAC), as well as external resources for training and other staff development options; - Improve the dissemination of and access to information about professional development options; - Create a directory of staff with specialized skills and/or knowledge to be posted on the website. | By June 2012 | Task Force with representatives of each committee and Administrative Council Lisa Maddalena, Admin., Heather Geddes, Chris Ricker, Monica Wilmot |  |
| - Explore options, including legal requirements, test alternatives, and develop a plan for recording and archiving training sessions for future viewing and use, including those offered by PLP. Include in the study the creation of a training library on the website. | - February 2012 | Technology Committee |  |

| Goals | Date to Complete | Leadership Team |
| --- | --- | --- |
| C. TECHNOLOGY |  |  |
| - Investigate technology for remote attendance to meetings and other service delivery options (workshops, etc.) - Explore options and funding for all member libraries to have access to the necessary tools to participate remotely. | - By February 2011 See A2. | Task Force with representatives of committees and the Administrative Council Technology Committee, Bill Rawson, Stacy DeMatteo |
| D. FUNDING AND ADVOCACY |  |  |
| - Negotiate with PLP the sustained support for regional (MOBAC) activities, including grants. | Ongoing | Jayanti Addleman and PLP staff |
| - DRAFT formal guidelines and tools for advocating for library services within the MOBAC region. | June 2012 | Administrative Council Task Force led by Kim Bui-Burton MegaMeeting, Teresa Landers, Peggy Mayfield |
| - Conduct a cost-benefit analysis of the PLP contract and other MOBAC expenses. | October 2012 | Budget Committee |
| E.. LOCAL IDENTITY |  |  |
| - Develop criteria and guidelines for creating committees. | June 2012 | Administrative Council / Committees Task Force Council Chairs Peggy Mayfield & Comm. Chairs |
| - Develop a position statement regarding resource sharing as a core function of MOBAC. | August 2012 | Jayanti Addleman, Ginny Steel and Kim Bui-Burton |

- =completed